## All Tasks
# | Feature Area | Lane | Task | Priority | Owner | Status | Notes
1 | Industry Type | UI | List view (name, code, active/inactive) with search |  |  | Not started
2 | Industry Type | UI | Add / Edit form |  |  | Not started
3 | Industry Type | UI | Delete / deactivate action |  |  | Not started
4 | Industry Type | Backend | Data model & migration |  |  | Not started
5 | Industry Type | Backend | GET list / GET by id |  |  | Not started
6 | Industry Type | Backend | POST create |  |  | Not started
7 | Industry Type | Backend | PATCH update |  |  | Not started
8 | Industry Type | Backend | DELETE |  |  | Not started
9 | Industry Type | Backend | Name/code uniqueness validation |  |  | Not started
10 | Industry Type | AI | Suggest an industry classification from an equipment description |  |  | Not started
11 | Industry Type | API integration | Wire list/CRUD UI to real endpoints |  |  | Not started
12 | Industry Type | API integration | Feed this list into Sensor & Tool Mapping dropdowns live |  |  | Not started
13 | Sensor | UI | List with search + industry filter + pagination |  |  | Not started
14 | Sensor | UI | Add Sensor form (name, industry type, parameters, protocol, description) |  |  | Not started
15 | Sensor | UI | Sensor detail/view page |  |  | Not started
16 | Sensor | UI | Edit form (pre-filled) |  |  | Not started
17 | Sensor | UI | Delete action |  |  | Not started
18 | Sensor | Backend | Data model & migration |  |  | Not started
19 | Sensor | Backend | GET list / GET by id |  |  | Not started
20 | Sensor | Backend | POST create |  |  | Not started
21 | Sensor | Backend | PATCH update |  |  | Not started
22 | Sensor | Backend | DELETE |  |  | Not started
23 | Sensor | Backend | sensorName uniqueness validation |  |  | Not started
24 | Sensor | AI | Auto-suggest telemetry parameters from a free-text sensor description |  |  | Not started
25 | Sensor | AI | Auto-classify industry type from sensor name/description |  |  | Not started
26 | Sensor | API integration | Wire list/CRUD UI to real endpoints |  |  | Not started
27 | Sensor | API integration | Populate Industry Type dropdown from live API |  |  | Not started
28 | Plant & Category | UI | Plant list + Add/Edit form (name, location, code) |  |  | Not started
29 | Plant & Category | UI | Category list/cards + Add/Edit form (name, code, engine type, fuel capacity, description, active toggle) |  |  | Not started
30 | Plant & Category | UI | Delete actions for both |  |  | Not started
31 | Plant & Category | UI | Search / filter on both lists |  |  | Not started
32 | Plant & Category | Backend | Data models & migrations — decide up front: is Category scoped to a Plant, or independent? |  |  | Not started
33 | Plant & Category | Backend | CRUD endpoints for Plant |  |  | Not started
34 | Plant & Category | Backend | CRUD endpoints for Category |  |  | Not started
35 | Plant & Category | Backend | Server-computed equipmentCount per plant/category |  |  | Not started
36 | Plant & Category | AI | Create a Plant or Category from a natural-language description ("two sites in Pune and Lucknow") |  |  | Not started
37 | Plant & Category | API integration | Wire both CRUDs to real endpoints |  |  | Not started
38 | Plant & Category | API integration | Feed Plant & Category dropdowns into Equipment/Device forms from live API |  |  | Not started
39 | Tool Mapping to Sensors | UI | List + search + industry filter |  |  | Not started
40 | Tool Mapping to Sensors | UI | Create/Edit form: name the profile, pick sensors from catalog, toggle active parameters per sensor |  |  | Not started
41 | Tool Mapping to Sensors | UI | Delete action |  |  | Not started
42 | Tool Mapping to Sensors | Backend | Data model — mapping references Sensor IDs + selected parameters |  |  | Not started
43 | Tool Mapping to Sensors | Backend | CRUD endpoints |  |  | Not started
44 | Tool Mapping to Sensors | Backend | Enforce name uniqueness if it's used as a matching key |  |  | Not started
45 | Tool Mapping to Sensors | AI | Match a device/equipment name against tool mapping names (exact, then fuzzy) to auto-suggest sensors |  |  | Not started
46 | Tool Mapping to Sensors | AI | Let chat create a new tool mapping on the fly when nothing matches |  |  | Not started
47 | Tool Mapping to Sensors | API integration | Resolve mapped sensors against real Sensor IDs, not denormalized names |  |  | Not started
48 | Tool Mapping to Sensors | API integration | Wire CRUD to real endpoints |  |  | Not started
49 | Equipment | UI | List + filters (status, onboarding status) + Add Equipment form |  |  | Not started
50 | Equipment | UI | Auto-fill spec fields (engine, fuel capacity, etc.) from selected Category |  |  | Not started
51 | Equipment | UI | Equipment Details / view page — spec sheet, location map, live parameters, error codes |  |  | Not started
52 | Equipment | UI | Edit action |  |  | Not started
53 | Equipment | UI | Delete action |  |  | Not started
54 | Equipment | Backend | Data model & migration |  |  | Not started
55 | Equipment | Backend | CRUD endpoints |  |  | Not started
56 | Equipment | Backend | Live telemetry ingestion & storage, if the details page shows live params |  |  | Not started
57 | Equipment | AI | Summarize equipment health/status from telemetry |  |  | Not started
58 | Equipment | AI | Predict maintenance needs from usage patterns |  |  | Not started
59 | Equipment | API integration | Wire CRUD + detail view to real records |  |  | Not started
60 | Equipment | API integration | Wire live parameters / error codes to a real telemetry feed |  |  | Not started
61 | Device | UI | Device list — metrics, filters, delete |  |  | Not started
62 | Device | UI | Device Setup / onboarding form (name, IMEI/serial, plant, vendor) |  |  | Not started
63 | Device | UI | Edit action, pre-filled with the existing device |  |  | Not started
64 | Device | UI | "Setup with AI" entry point |  |  | Not started
65 | Device | Backend | Data model & migration |  |  | Not started
66 | Device | Backend | CRUD endpoints |  |  | Not started
67 | Device | Backend | IMEI/serial uniqueness validation |  |  | Not started
68 | Device | Backend | Device ↔ Equipment / Tool Mapping association |  |  | Not started
69 | Device | AI | Match device name/model against Tool Mappings to auto-populate sensors |  |  | Not started
70 | Device | AI | Guided AI onboarding of a new device end-to-end |  |  | Not started
71 | Device | API integration | Wire CRUD to real endpoints |  |  | Not started
72 | Device | API integration | Decide whether server or client resolves the Tool Mapping match at write time |  |  | Not started
73 | AI Onboarding | UI | Session list — status, progress, search/filter |  |  | Not started
74 | AI Onboarding | UI | Chat interface — message thread, quick-action prompts, live setup-status panel |  |  | Not started
75 | AI Onboarding | UI | Equipment/device detail "view" screens reachable from the chat |  |  | Not started
76 | AI Onboarding | Backend | Session persistence — a session survives refresh and is resumable |  |  | Not started
77 | AI Onboarding | Backend | Endpoints to create Plant/Category/Equipment/Device/Tool Mapping records as the conversation progresses |  |  | Not started
78 | AI Onboarding | Backend | Store per-session setup-status progress server-side |  |  | Not started
79 | AI Onboarding | AI | Real LLM/NLU integration to parse free text into structured records |  |  | Not started
80 | AI Onboarding | AI | Multi-turn conversation state management |  |  | Not started
81 | AI Onboarding | AI | Drive setup-status steps from real backend progress, not a scripted heuristic |  |  | Not started
82 | AI Onboarding | API integration | Wire chat actions to real create/update calls for each resource |  |  | Not started
83 | AI Onboarding | API integration | Real QR code generation if session labels get printed/scanned |  |  | Not started

## Summary
Feature Area | UI tasks | Backend tasks | AI tasks | API integration tasks | Total
Industry Type | 3 | 6 | 1 | 2 | 12
Sensor | 5 | 6 | 2 | 2 | 15
Plant & Category | 4 | 4 | 1 | 2 | 11
Tool Mapping to Sensors | 3 | 3 | 2 | 2 | 10
Equipment | 5 | 3 | 2 | 2 | 12
Device | 4 | 4 | 2 | 2 | 12
AI Onboarding | 3 | 3 | 3 | 2 | 11
Total | 27 | 29 | 13 | 14 | 83